## wo sign
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
2nd QUARTER, CY 2025
PROVINCE OF DAVAO DEL NORTE
PROGRAM OR PROJECT |  |  |  |  | LOCATION | APPROPRIATION | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | REMARKS
[9 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
NATIONAL TAX ALLOTMENT
ANNUAL BUDGET:
OTHER PURPOSES:
DEBT SERVICING PROGRAM
|  |  | Loans Payable - Domestic |  |  | 201715883 |  |  | 45.39% | 91567154.99
|  |  | Interest Expenses |  |  | 73526154 |  |  | 41.66% | 30631902.48
|  | TOTAL DEBT SERVICING PROGRAM |  |  |  | 275242037 |  |  |  | 122199057.47
GENERAL PUBLIC SERVICES
GOVERNMENT FACILITIES UPGRADING PROGRAM (1999)
UPGRADING OF VARIOUS GOV'T. BUILDINGS/FACILITIES
|  |  |  | Re-roofing of PENRO Building | TAGUM CITY | 500000 |  |  | 0% |  |  | PROCUREMENT ON PROCESS
|  |  |  | Improvement of PGSO Depot (Completion) | TAGUM CITY | 1000000 | 04/01/2025 |  | 4.394% | 43944.28 |  | ON GOING
|  |  |  | Improvement of Provincial Capitol Public Toilets (Phase 1) | TAGUM CITY | 1000000 |  |  | 0% |  |  | POW PREPARATION
|  |  |  | Improvement of PRC Facility ( Completion) | TAGUM CITY | 1500000 |  |  | 0% |  |  | POW PREPARATION
|  |  |  | Other Structures-Improvement of PGSO Powerhouse w/ Jantorial Lounge | TAGUM CITY | 1000000 |  |  | 0% |  |  | POW PREPARATION
|  |  | TOTAL UPGRADING OF VARIOUS GOV'T. BLDGS./FACILITIES |  |  | 5000000 |  |  |  | 43944.28
GOV'T. CENTER GROUND DEV'T. PROJECT (Phase 20)
|  |  |  | Improvement of SP Parking Area Carport | TAGUM CITY | 1500000 |  |  | 0% |  |  | POW PREPARATION
|  |  |  | Installation of Streetlights with Solar Panels (Phase 2) | TAGUM CITY | 1000000 | 04/01/2025 |  | 85.68% | 856824.51 |  | ON GOING
|  |  |  | Landscaping of PGSO Nursery (Phase II) | TAGUM CITY | 1500000 |  |  | 0% |  |  | POW PREPARATION
|  |  |  | Rehabilitation of Concrete Fence from OMMA/NCIP to PRC (Phase II) | TAGUM CITY | 2500000 | 2025-04-01 |  | 10.63% | 265649.26 |  | ON GOING
|  |  | TOTAL GOV'T. CENTER GROUND DEV'T. PROJECT (Phase 19) |  |  | 6500000 |  |  |  | 1122473.77
HEALTH SERVICES
DISEASE PREVENTION AND CONTROL PROGRAM (4919)
|  |  | PREVENTION & CONTROL OF COMMUNICABLE DISEASE PROJECT |  |  | 8340000 |  |  | 2.4% | 200186.78 |  | ON PROCESS
|  |  | PREVENTION & CONTROL OF NON-COMMUNICABLE DISEASE PROJECT |  |  | 1530100 |  |  | 3.767% | 57645 |  | ON PROCESS
|  | TOTAL DISEASE PREVENTION AND CONTROL PROGRAM |  |  |  | 9870100 |  |  |  | 257831.78
ECONOMIC SERVICES
FOOD SUFFICIENCY PROGRAM (8911)
|  |  | FISHERY ENHANCEMENT PROJECT |  |  | 500000 | 02/28/2025 | 2025-12-31 | 88.72% | 443617.8 |  | Bidding procurement for feeds worth 342.750.00 and Hito fingerlings worth 100,867.80 is already delivered and used at Provincial Freshwater Hatchery for fingerlings production
|  |  | HIGH VALUE CROPS DEVELOPMENT PROJECT |  |  | 9378950 | 02/02/2025 | 2026-01-01 | 29.7% | 2785505 |  | Bidding procurement of vegetable seeds awarded to CMC Enterprises worth 1,577,810 is for delivery , and 505 bags complete fertilizer awarded to PRB Agricultural Products worth 1,009,495.00 is already delivered and for distribution to the identified recipients.
|  |  | AGRICULTURAL SUPPORT SERVICES PROJECT |  |  | 1010000 | 02/13/2025 | 2026-01-02 | 38.48% | 388626 |  | Supplies are delivered for PAGRO laboratory production
|  |  | ON-FARM RESEARCH PROJECT |  |  | 235500 | 02/20/2025 | 2026-01-03 | 59.8% | 140829 |  | On going conduct of researches for the established demonstration farm
|  |  | SUPPORT TO BOOST LIVESTOCK AND POULTRY INDUSTRY PROJECT |  |  | 986368 | 02/26/2025 | 2026-01-04 | 3.792% | 37400 |  | The delayed procurements of the supplies was due to the change made on the procurement scheduled from 1st sem to 2nd sem of this year. Since the supplies and materials from 2024 Supplemental Budget was used for the continued project implementation
|  | TOTAL FOOD SUFFICIENCY PROGRAM |  |  |  | 12110818 |  |  |  | 3795977.8
LIVESTOCK DEVELOPMENT PROGRAM (8911)
|  |  | ANIMAL HEALTH CARE & DISEASE MGT. PROJECT |  |  | 300000 | 2025-02-01 | 11/28/2025 | 20.88% | 62647 |  | The procurement is on-going, and the related activities are scheduled to be conducted in the 3rd and 4th quarters.
|  |  | RABIES CONTROL & PREVENTION PROJECT |  |  | 300000 | 2025-03-01 | 11/28/2025 | 86.33% | 259000 |  | The disbursement is in process, and the related activities are scheduled to be conducted in the 3rd and 4th quarters.
|  | TOTAL LIVESTOCK DEVELOPMENT PROGRAM |  |  |  | 600000 |  |  |  | 321647
INTEGRATED WATERSHED DEVELOPMENT PROGRAM (8911)
|  |  | CAVE MANAGEMENT PROJECT |  |  | 84800 | 2025-01-20 |  | 89.55% | 75936 |  | Payment on Process
|  |  | AGROFORESTRY MANAGEMENT PROJECT |  |  | 304755 | 2025-04-02 |  | 46.02% | 140250 |  | Payment on Process
|  |  | TREE PLANTATION MANAGEMENT PROJECT |  |  | 531500 | 2025-01-20 |  | 34.24% | 181992 |  | Payment on Process
|  |  | COMMUNITY TREE PARKS MANAGEMENT PROJECT |  |  | 69950 | 2025-01-20 |  | 86.98% | 60840 |  | Payment on Process
|  |  | PANTARON MOUNTAIN RANGE MANAGEMENT PROJECT |  |  | 500000 | 2025-01-20 |  | 88.05% | 440250 |  | for Delivery
|  | TOTAL INTEGRATED WATERSHED DEVELOPMENT PROGRAM |  |  |  | 1491005 |  |  |  | 899268
INFRASTRUCTURE DEVELOPMENT PROGRAM
REPAIRS & MAINTENANCE OF PROVINCIAL ROADS-DIST. I
|  |  |  | JCT. HIGHWAY MAGATOS - NEW BANTAYAN |  | 968974.54 | 2025-01-02 | 2025-12-29 | 52.02% | 504092.27 |  | ON GOING
|  |  |  | MAGATOS - BDRY. PAGSABANGAN |  | 1136839.15 | 2025-01-02 | 2025-12-29 | 53.93% | 613048.5 |  | ON GOING
|  |  |  | ILOG - NEW BANTAYAN |  | 373678.14 | 2025-01-02 | 2025-12-29 | 54.24% | 202668.64 |  | ON GOING
|  |  |  | ASUNCION - MONTE CARLO - DEL PILAR |  | 719297.52 | 2025-01-02 | 2025-12-29 | 40.03% | 287952.54 |  | ON GOING
|  |  |  | JCT. HIGHWAY CANATAN - MAGATOS |  | 677313.65 | 2025-01-02 | 2025-12-29 | 54.82% | 371317.57 |  | ON GOING
|  |  |  | SAUG-SONLON-BDRY. LONGANAPAN |  | 1192397.8 | 2025-01-02 | 2025-12-29 | 58.39% | 696286.1 |  | ON GOING
|  |  |  | JCT. NEW VISAYAS - BUAN |  | 329081.54 | 2025-01-02 | 2025-12-29 | 53.73% | 176806.82 |  | ON GOING
|  |  |  | KAPALONG-MABANTAO-FLORIDA |  | 1045246.62 | 2025-01-02 | 2025-12-29 | 58.23% | 608629.05 |  | ON GOING
|  |  |  | JCT. HIGHWAY GABUYAN - SEMONG - DAGOHOY |  | 978439.76 | 2025-01-02 | 2025-12-29 | 55.91% | 547019.25 |  | ON GOING
|  |  |  | SEMONG - PALMA GIL |  | 300465.75 | 2025-01-02 | 2025-12-29 | 52.47% | 157642.95 |  | ON GOING
|  |  |  | STO. NIÑO-PALMA GIL-SITIO OPAO |  | 224149.64 | 2025-01-02 | 2025-12-29 | 47.74% | 107018.67 |  | ON GOING
|  |  |  | DALIGDIGON-DAGOHOY |  | 143783.32 | 2025-01-02 | 2025-12-29 | 31.32% | 45036.25 |  | ON GOING
|  |  |  | CAPUNGAGAN - MABUHAY - PANDULIAN |  | 637559.72 | 2025-01-02 | 2025-12-29 | 56.17% | 358148.89 |  | ON GOING
|  |  |  | PANDULIAN - JCT. SAN MIGUEL |  | 196524.41 | 2025-01-02 | 2025-12-29 | 47.1% | 92556.25 |  | ON GOING
|  |  |  | FLORIDA- NEW BOHOLANO |  | 237026.76 | 2025-01-02 | 2025-12-29 | 43.32% | 102672.82 |  | ON GOING
|  |  |  | JCT. NEW BOHOLANO - NEW LOON |  | 587988.37 | 2025-01-02 | 2025-12-29 | 52.9% | 311036.89 |  | ON GOING
|  |  |  | KM. 9, SAGAYEN-SAWATA |  | 794638.37 | 2025-01-02 | 2025-12-29 | 59.61% | 473686.19 |  | ON GOING
|  |  |  | KM. 15, KIPALILI - NEW LOON |  | 958981.03 | 2025-01-02 | 2025-12-29 | 52.08% | 499472.5 |  | ON GOING
|  |  |  | SAWATA-LIBUTON-MONTE DUJALI-PATEL SEGMENT 1 |  | 1857736.84 | 2025-01-02 | 2025-12-29 | 58.4% | 1084938.07 |  | ON GOING
|  |  |  | SAWATA-MAMANGAN-PINAMUNO |  | 1994652.37 | 2025-01-02 | 2025-12-29 | 52.72% | 1051671.81 |  | ON GOING
|  |  |  | IGANGON - SAWATA |  | 404010.88 | 2025-01-02 | 2025-12-29 | 32.69% | 132069.14 |  | ON GOING
|  |  |  | TAGAYTAY-BUAN |  | 571963.52 | 2025-01-02 | 2025-12-29 | 69.44% | 397143.25 |  | ON GOING
|  |  |  | LIMBAAN-STA. FE- EL SALVADOR |  | 2251490.05 | 2025-01-02 | 2025-12-29 | 75.17% | 1692550.75 |  | ON GOING
|  |  |  | DEL PILAR-JCT. SILANGAN |  | 569101.95 | 2025-01-02 | 2025-12-29 | 66.41% | 377941.25 |  | ON GOING
|  |  |  | NEW CORELLA - NEW SAMBOG - SILANGAN |  | 700558.47 | 2025-01-02 | 2025-12-29 | 67.56% | 473266.89 |  | ON GOING
|  |  |  | POB. NEW CORELLA - PRK. 10 POB. |  | 54369.99 | 2025-01-02 | 2025-12-29 | 11.82% | 6426.25 |  | ON GOING
|  |  |  | PRK. 7 POB. - NEW SAMBOG |  | 257498.05 | 2025-01-02 | 2025-12-29 | 61.66% | 158762.5 |  | ON GOING
|  |  |  | NEW CORELLA-GUADALUPE-DEL MONTE |  | 1247648.28 | 2025-01-02 | 2025-12-29 | 73.99% | 923164.5 |  | ON GOING
|  |  |  | STA. FE- DEL MONTE |  | 367602.79 | 2025-01-02 | 2025-12-29 | 45.46% | 167113.75 |  | ON GOING
|  |  |  | NEW CORELLA- NEW BOHOL |  | 590651.84 | 2025-01-02 | 2025-12-29 | 55.34% | 326862.3 |  | ON GOING
|  |  |  | CARCOR- JCT. KAUSWAGAN |  | 494480.78 | 2025-01-02 | 2025-12-29 | 51.75% | 255906.21 |  | ON GOING
|  |  |  | DEL PILAR- PRK. 9 BAGSAK-SAN JOSE |  | 536039.71 | 2025-01-02 | 2025-12-29 | 61.93% | 331948.14 |  | ON GOING
|  |  |  | SAN JUAN- NEW TALISAY |  | 700118.23 | 2025-01-02 | 2025-12-29 | 57.92% | 405509.59 |  | ON GOING
|  |  |  | SAN JUAN- KAUSWAGAN- NEW CORTEZ |  | 142902.83 | 2025-01-02 | 2025-12-29 | 13.85% | 19791.25 |  | ON GOING
|  |  |  | NEW BOHOL - JCT. EL UNIDO |  | 243894.55 | 2025-01-02 | 2025-12-29 | 47.57% | 116019.25 |  | ON GOING
|  |  |  | NEW CORELLA- EL UNIDO- JCT. MESAOY |  | 960081.64 | 2025-01-02 | 2025-12-29 | 49.02% | 470618.14 |  | ON GOING
|  |  |  | MESAOY-DASING |  | 189700.65 | 2025-01-02 | 2025-12-29 | 51.65% | 97976.5 |  | ON GOING
|  |  |  | JCT. SAN JUAN- JCT. MESAOY |  | 224347.76 | 2025-01-02 | 2025-12-29 | 43.32% | 97196.89 |  | ON GOING
|  |  |  | MESAOY- JCT. MAHAYAHAY |  | 575727.61 | 2025-01-02 | 2025-12-29 | 47.34% | 272534.64 |  | ON GOING
|  |  |  | MESAOY- NEW BOHOL |  | 692766.17 | 2025-01-02 | 2025-12-29 | 48.18% | 333764.75 |  | ON GOING
|  |  |  | NEW VISAYAS-BINANCIAN |  | 171034.35 | 2025-01-02 | 2025-12-29 | 23.6% | 40356.73 |  | ON GOING
|  |  |  | DATU BALONG- PRK. MAMALIAN |  | 76162.02 | 2025-01-02 | 2025-12-29 | 24.91% | 18974.49 |  | ON GOING
|  |  |  | PUROK 7 POBLACION-LIMBAAN |  | 167688.51 | 2025-01-02 | 2025-12-29 | 22.54% | 37796.89 |  | ON GOING
|  |  |  | LIMBAAN- MACGUM |  | 196876.61 | 2025-01-02 | 2025-12-29 | 4.857% | 9563.28 |  | ON GOING
|  |  |  | JCT. HIGHWAY CANATAN- DOÑA ANDREA |  | 592302.75 | 2025-01-02 | 2025-12-29 | 66.44% | 393509.25 |  | ON GOING
|  |  |  | STA. FELOMINA- SAN ROQUE |  | 879076.94 | 2025-01-02 | 2025-12-29 | 67.82% | 596152.5 |  | ON GOING
|  |  |  | JCT. SAGAYEN - SONLON |  | 1733302.19 | 2025-01-02 | 2025-12-29 | 69.67% | 1207661.22 |  | ON GOING
|  |  |  | SAN VICENTE- BUTAY |  | 893560.94 | 2025-01-02 | 2025-12-29 | 59.9% | 535223.05 |  | ON GOING
|  |  |  | JCT. HIGHWAY DOÑA ANDREA - CAPUNGAGAN |  | 1187335 | 2025-01-02 | 2025-12-29 | 64.98% | 771495.64 |  | ON GOING
|  |  |  | PAMACAUN- LASANG- BANATE |  | 412331.47 | 2025-01-02 | 2025-12-29 | 70.51% | 290740.05 |  | ON GOING
|  |  |  | ANGELO - DAGOHOY |  | 48206.59 | 2025-01-02 | 2025-12-29 | 10.54% | 5080 |  | ON GOING
|  |  |  | DALIGDIGON- LUMABAG |  | 310371.22 | 2025-01-02 | 2025-12-29 | 62.88% | 195151.39 |  | ON GOING
|  |  |  | STO. NIÑO- DALIGDIGON- PAITON |  | 1317646.88 | 2025-01-02 | 2025-12-29 | 70.85% | 933517.17 |  | ON GOING
|  |  |  | JCT. PAITON- MIBOLO |  | 2735669.16 | 2025-01-02 | 2025-12-29 | 68.08% | 1862402.6 |  | ON GOING
|  |  |  | JCT. SAMPAO- BDRY. MAMACAO |  | 679646.93 | 2025-01-02 | 2025-12-29 | 67.94% | 461782.51 |  | ON GOING
|  |  |  | JCT. HIGHWAY LUNA- MAMACAO- NARRA |  | 918588.75 | 2025-01-02 | 2025-12-29 | 59.52% | 546782.97 |  | ON GOING
|  |  |  | JCT. GABUYAN - KATIPUNAN - BUCANA |  | 726048.53 | 2025-01-02 | 2025-12-29 | 57.31% | 416074.45 |  | ON GOING
|  |  |  | FLORIDA-SUAON- JCT. GUPITAN |  | 1893792.73 | 2025-01-02 | 2025-12-29 | 71.63% | 1356433.75 |  | ON GOING
|  |  |  | JCT. SUAON - LIBUTON |  | 271673.87 | 2025-01-02 | 2025-12-29 | 44.42% | 120670.25 |  | ON GOING
|  |  |  | JCT. DACUDAO- MABUHAY |  | 117016.55 | 2025-01-02 | 2025-12-29 | 32.1% | 37558.75 |  | ON GOING
|  |  |  | MONTE DUJALI - GUPITAN |  | 433639.22 | 2025-01-02 | 2025-12-29 | 52.29% | 226740 |  | ON GOING
|  |  |  | JCT. PATEL- LANGAN |  | 156902.56 | 2025-01-02 | 2025-12-29 | 36.41% | 57122.43 |  | ON GOING
|  |  |  | DATU BALONG- PINAMUNO |  | 289503.71 | 2025-01-02 | 2025-12-29 | 62.61% | 181262.49 |  | ON GOING
|  |  |  | JCT. SAWATA - BDRY. BINASBAS |  | 52653.05 | 2025-01-02 | 2025-12-29 | 53.73% | 28292.89 |  | ON GOING
|  |  |  | NEW CORELLA- STO. NIÑO-MACGUM |  | 1515910.27 | 2025-01-02 | 2025-12-29 | 68.6% | 1039934.16 |  | ON GOING
|  |  |  | STA. FE- MAMBING |  | 815065.63 | 2025-01-02 | 2025-12-29 | 67.07% | 546643.97 |  | ON GOING
|  |  |  | NEW CORELLA- SAUG |  | 1009697.01 | 2025-01-02 | 2025-12-29 | 55.75% | 562875.39 |  | ON GOING
|  |  |  | LIMBAAN- STO NIÑO |  | 393224.93 | 2025-01-02 | 2025-12-29 | 53.88% | 211868.14 |  | ON GOING
|  |  |  | JCT. MONTE CARLO - UPPER CABAYWA- CANATAN |  | 527454.98 | 2025-01-02 | 2025-12-29 | 52.07% | 274637 |  | ON GOING
|  |  |  | CARCOR- PATROCENIO- JCT. BAYABAS |  | 1027172.01 | 2025-01-02 | 2025-12-29 | 70.73% | 726549.82 |  | ON GOING
|  |  |  | DEL PILAR-EL UNIDO |  | 110412.91 | 2025-01-02 | 2025-12-29 | 41.05% | 45320 |  | ON GOING
|  |  |  | BRDY. TAGUM-BACA- NEW CORELLA |  | 646606.71 | 2025-01-02 | 2025-12-29 | 62.61% | 404820.55 |  | ON GOING
|  |  |  | JCT. CARCOR - PRK. 9 BAGSAK |  | 264145.72 | 2025-01-02 | 2025-12-29 | 56.82% | 150100 |  | ON GOING
|  |  |  | CARCOR- PUROK 7 POBLACION |  | 55734.75 | 2025-01-02 | 2025-12-29 | 2.871% | 1600 |  | ON GOING
|  |  |  | ASUNCION- NEW ALEGRIA- BDRY. CUAMBOGAN |  | 267711.69 | 2025-01-02 | 2025-12-29 | 54.76% | 146600 |  | ON GOING
|  |  |  | SONLON- NEW VISAYAS- CAMANSA |  | 199958.31 | 2025-01-02 | 2025-12-29 | 50.31% | 100600 |  | ON GOING
|  |  |  | PRK. 1 MAUNLOM- PRK. 6 MAUNLOM |  | 376143.5 | 2025-01-02 | 2025-12-29 | 54.24% | 204001.9 |  | ON GOING
|  |  | TOTAL REPAIRS & MAINT. OF PROVINCIAL ROADS-DIST. I |  |  | 50600000 |  |  |  | 30094163.65
REPAIRS & MAINTENANCE OF PROVINCIAL ROADS-DIST. II
|  |  |  | CEBULANO- MANGALCAL |  | 383927.31 | 2025-01-02 | 2025-12-29 | 64.22% | 246552.53 |  | ON GOING
|  |  |  | TUBOD - BASA - MANGALCAL |  | 361830.78 | 2025-01-02 | 2025-12-29 | 4.414% | 15972.44 |  | ON GOING
|  |  |  | JCT. HIGHWAY CARMEN-MANGALCAL-TUBOD |  | 1044061.33 | 2025-01-02 | 2025-12-29 | 75.28% | 785963.63 |  | ON GOING
|  |  |  | ISING-ST.NIÑO |  | 190582.62 | 2025-01-02 | 2025-12-29 | 14.97% | 28525.71 |  | ON GOING
|  |  |  | TUGANAY-TABA |  | 393134.2 | 2025-01-02 | 2025-12-29 | 94.84% | 372837.69 |  | ON GOING
|  |  |  | NEW CAMILING - ALEJAL - LOWER MAGSAYSAY |  | 619623.7 | 2025-01-02 | 2025-12-29 | 77.49% | 480121.65 |  | ON GOING
|  |  |  | JCT HIGHWAY-TUGANAY-ANIBONGAN |  | 336972.17 | 2025-01-02 | 2025-12-29 | 4.74% | 15972.45 |  | ON GOING
|  |  |  | MABAUS - CABAY-ANGAN |  | 294620.48 | 2025-01-02 | 2025-12-29 | 10.58% | 31158.82 |  | ON GOING
|  |  |  | JCT. HIGHWAY GUADALUPE - BDRY. TAGUM |  | 727344.31 | 2025-01-02 | 2025-12-29 | 81.19% | 590524.38 |  | ON GOING
|  |  |  | POBLACION DUJALI - PRK. 8 DUJALI |  | 754964.98 | 2025-01-02 | 2025-12-29 | 98.12% | 740783.14 |  | ON GOING
|  |  |  | PRK 1- PRK 2 SITIO PAWAS |  | 128896.46 | 2025-01-02 | 2025-12-29 | 10.56% | 13610.69 |  | ON GOING
|  |  |  | BACALI - CASIG-ANG - LIBERTAD |  | 432723.83 | 2025-01-02 | 2025-12-29 | 76.28% | 330094.55 |  | ON GOING
|  |  |  | PRK.MAGSAYSAY- LUNGA-OG- DALISAY |  | 258713.61 | 2025-01-02 | 2025-12-29 | 6.174% | 15972.44 |  | ON GOING
|  |  |  | PRK.APITONG-UPPER BALISONG-DALISAY |  | 423516.94 | 2025-01-02 | 2025-12-29 | 3.771% | 15972.44 |  | ON GOING
|  |  |  | LOS AMIGOS 1 - ESPERANZA - LOS AMIGOS 2 |  | 330481.32 | 2025-01-02 | 2025-12-29 | 4.833% | 15972.44 |  | ON GOING
|  |  |  | NEW KATIPUNAN- PANTARON |  | 180455.04 | 2025-01-02 | 2025-12-29 | 5.611% | 10125.32 |  | ON GOING
|  |  |  | FD RD 3 - KINAMON - LUNA |  | 1082730.26 | 2025-01-02 | 2025-12-29 | 61.85% | 669660.39 |  | ON GOING
|  |  |  | ISING- SADPODON- TABA- DILADILA |  | 522951.35 | 2025-01-02 | 2025-12-29 | 59.1% | 309056.22 |  | ON GOING
|  |  |  | ALEJAL - ALEMAG |  | 164803.33 | 2025-01-02 | 2025-12-29 | 0% | 0 |  | ON GOING
|  |  |  | TUGANAY - ANIBONGAN - SAN ISIDRO |  | 664737.46 | 2025-01-02 | 2025-12-29 | 83.08% | 552242.47 |  | ON GOING
|  |  |  | DALISAY - MABUHAY |  | 299223.93 | 2025-01-02 | 2025-12-29 | 3.894% | 11651.74 |  | ON GOING
|  |  |  | DUJALI-BALISONG- MAGUPISING |  | 922780.17 | 2025-01-02 | 2025-12-29 | 83.54% | 770850.2 |  | ON GOING
|  |  |  | DUJALI-SAN MIGUEL |  | 363672.16 | 2025-01-02 | 2025-12-29 | 69.07% | 251177.17 |  | ON GOING
|  |  |  | UPPER MANGALCAL-LOWER MANGALCAL |  | 223727.43 | 2025-01-02 | 2025-12-29 | 7.139% | 15972.44 |  | ON GOING
|  |  |  | CEBULANO - LOCETA |  | 172168.84 | 2025-01-02 | 2025-12-29 | 12.68% | 21822.46 |  | ON GOING
|  |  |  | MALIGAYA-NEW CAMILING |  | 196106.76 | 2025-01-02 | 2025-12-29 | 13.62% | 26702.64 |  | ON GOING
|  |  |  | ANAHAW- MALIGAYA |  | 441930.72 | 2025-01-02 | 2025-12-29 | 15.93% | 70398.78 |  | ON GOING
|  |  |  | ANIBONGAN-GUADALUPE |  | 228330.87 | 2025-01-02 | 2025-12-29 | 7.732% | 17655.34 |  | ON GOING
|  |  |  | JCT. ANIBONGAN- PRK 2,7,5 SAN ISIDRO |  | 289096.35 | 2025-01-02 | 2025-12-29 | 5.832% | 16858.8 |  | ON GOING
|  |  |  | NEW CASAY - BUGTONG TALISAY |  | 200710.2 | 2025-01-02 | 2025-12-29 | 7.958% | 15972.44 |  | ON GOING
|  |  |  | PRK. 5 RJS - PRK. 6 NEW CASAY |  | 251348.1 | 2025-01-02 | 2025-12-29 | 64.25% | 161482.49 |  | ON GOING
|  |  |  | DUJALI SITIO PAWAS |  | 115086.13 | 2025-01-02 | 2025-12-29 | 15.46% | 17790.85 |  | ON GOING
|  |  |  | DUJALI- PAWAS- SAN VICENTE |  | 406944.54 | 2025-01-02 | 2025-12-29 | 8.51% | 34632.44 |  | ON GOING
|  |  |  | JCT. SALVACION- SAN VICENTE- CABAY-ANGAN |  | 317637.71 | 2025-01-02 | 2025-12-29 | 17.67% | 56132.78 |  | ON GOING
|  |  |  | SAN MIGUEL - CASIG-ANG |  | 234775.7 | 2025-01-02 | 2025-12-29 | 41.29% | 96928.2 |  | ON GOING
|  |  |  | KINAMAYAN - MOSLOG - MAHAYAG |  | 297382.55 | 2025-01-02 | 2025-12-29 | 5.818% | 17300.28 |  | ON GOING
|  |  |  | SAN MIGUEL - MOSLOG KINAMAYAN |  | 266999.81 | 2025-01-02 | 2025-12-29 | 6.024% | 16083.24 |  | ON GOING
|  |  |  | KINAMAYAN LUNGA-OG |  | 238458.45 | 2025-01-02 | 2025-12-29 | 1.306% | 3113.41 |  | ON GOING
|  |  |  | SITIO PARADISE - MAGKAKAISA - ESPERANZA |  | 161120.58 | 2025-01-02 | 2025-12-29 | 56.55% | 91109.55 |  | ON GOING
|  |  |  | MUGAS - LANATAD |  | 140865.42 | 2025-01-02 | 2025-12-29 | 18.44% | 25973.74 |  | ON GOING
|  |  |  | MUGAS - LUNGA - OG |  | 246744.65 | 2025-01-02 | 2025-12-29 | 8.318% | 20524.04 |  | ON GOING
|  |  |  | PANTARON - MUGAS |  | 308430.82 | 2025-01-02 | 2025-12-29 | 5.179% | 15972.44 |  | ON GOING
|  |  |  | FD RD 3 SAN JOSE |  | 435489.5 | 2025-01-02 | 2025-12-29 | 80.44% | 350306.1 |  | ON GOING
|  |  |  | NAFCO - BOBONGON |  | 244903.27 | 2025-01-02 | 2025-12-29 | 2.494% | 6106.73 |  | ON GOING
|  |  |  | JCT. BDRY. TAGUM TALOMO |  | 786007.49 | 2025-01-02 | 2025-12-29 | 98.74% | 776141.78 |  | ON GOING
|  |  |  | JCT. HIGHWAY-ST.NINO - CEBULANO |  | 192424 | 2025-01-02 | 2025-12-29 | 0% | 0 |  | ON GOING
|  |  |  | JCT. HIGHWAY - TUBOD - BAGONG SILANG |  | 172168.84 | 2025-01-02 | 2025-12-29 | 9.212% | 15860 |  | ON GOING
|  |  |  | BASA-TUBOD |  | 143627.48 | 2025-01-02 | 2025-12-29 | 12.02% | 17260 |  | ON GOING
|  |  |  | TUBOD - PILAR |  | 142706.8 | 2025-01-02 | 2025-12-29 | 2.07% | 2954.55 |  | ON GOING
|  |  |  | LOCETA -LOWER MANGALCAL |  | 190582.62 | 2025-01-02 | 2025-12-29 | 5.607% | 10686.28 |  | ON GOING
|  |  |  | LOWER ASUNCION - UPPER ASUNCION |  | 93910.28 | 2025-01-02 | 2025-12-29 | 1.888% | 1772.73 |  | ON GOING
|  |  |  | JCT. HIGHWAY- ISING- MAGSAYSAY |  | 998026.88 | 2025-01-02 | 2025-12-29 | 99.01% | 988161.17 |  | ON GOING
|  |  |  | ANIBONGAN- SALVACION- CABAY-ANGAN |  | 638037.48 | 2025-01-02 | 2025-12-29 | 95.72% | 610709.57 |  | ON GOING
|  |  |  | MABAUS- SALVACION |  | 127055.08 | 2025-01-02 | 2025-12-29 | 13.31% | 16910 |  | ON GOING
|  |  |  | SITIO MALAGA- TIBULAO |  | 296461.86 | 2025-01-02 | 2025-12-29 | 96.67% | 286596.15 |  | ON GOING
|  |  |  | DUJALI- TANGLAW |  | 331448.04 | 2025-01-02 | 2025-12-29 | 7.835% | 25969.93 |  | ON GOING
|  |  |  | DUJALI- SAN ISIDRO |  | 595946.7 | 2025-01-02 | 2025-12-29 | 55.56% | 331110.25 |  | ON GOING
|  |  |  | CABAY-ANGAN - ESPERANZA |  | 494409.99 | 2025-01-02 | 2025-12-29 | 83.38% | 412223.56 |  | ON GOING
|  |  |  | PRK 5- PRK. 1 PAWAS- DUJALI |  | 200710.2 | 2025-01-02 | 2025-12-29 | 17.46% | 35038.34 |  | ON GOING
|  |  |  | PRK 6 CABAY-ANGAN- ESTI |  | 99434.41 | 2025-01-02 | 2025-12-29 | 24.06% | 23924.41 |  | ON GOING
|  |  |  | PRK NARAFIL- BRGY SITE MAGUPISING |  | 191503.31 | 2025-01-02 | 2025-12-29 | 13.95% | 26709.03 |  | ON GOING
|  |  |  | SAN MIGUEL - CROSSING KINAMAYAN |  | 257792.92 | 2025-01-02 | 2025-12-29 | 4.168% | 10744.27 |  | ON GOING
|  |  |  | SAN MIGUEL - LIBERTAD |  | 570827.18 | 2025-01-02 | 2025-12-29 | 98.27% | 560961.47 |  | ON GOING
|  |  |  | FD. RD. 2- STO. TOMAS- MAGWAWA |  | 940023.47 | 2025-01-02 | 2025-12-29 | 98.95% | 930157.76 |  | ON GOING
|  |  |  | JCT. HIGHWAY- BUGTONG LUBI- BALAGUNAN |  | 255030.85 | 2025-01-02 | 2025-12-29 | 6.733% | 17171.11 |  | ON GOING
|  |  |  | JCT. HIGHWAY- BALAGUNAN |  | 278968.77 | 2025-01-02 | 2025-12-29 | 5.279% | 14725.46 |  | ON GOING
|  |  |  | JCT.HIGHWAY - TANGLAW |  | 366434.22 | 2025-01-02 | 2025-12-29 | 86.18% | 315795.72 |  | ON GOING
|  |  |  | KIMAMON - LUNGA-OG - TALOMO |  | 551492.71 | 2025-01-02 | 2025-12-29 | 98.21% | 541627 |  | ON GOING
|  |  |  | BDRY TAGUM- CROSSING KINAMAYAN-STO. TOMAS |  | 1332904.13 | 2025-01-02 | 2025-12-29 | 94.15% | 1254995.85 |  | ON GOING
|  |  |  | PRK. NARAFIL- PRK. DAISY MAGUPISING |  | 69512.26 | 2025-01-02 | 2025-12-29 | 20.15% | 14008.26 |  | ON GOING
|  |  |  | SAN JOSE- SITIO MAHAYAHAY,MAGWAWA |  | 196106.56 | 2025-01-02 | 2025-12-29 | 0% | 0 |  | ON GOING
|  |  |  | STO. TOMAS- BDRY. MAMACAO |  | 451137.61 | 2025-01-02 | 2025-12-29 | 97.81% | 441271.9 |  | ON GOING
|  |  |  | JCT. HIGHWAY- STO. NIÑO- LA PAZ- SAN VICENTE |  | 559778.91 | 2025-01-02 | 2025-12-29 | 73.13% | 409377.82 |  | ON GOING
|  |  |  | JCT. HIGHWAY- STO NIÑO- KABANKALAN- LA PAZ |  | 362795.76 | 2025-01-02 | 2025-12-29 | 84.52% | 306623.42 |  | ON GOING
|  |  |  | JCT. HWAY- TUGANAY-TABA |  | 405103.16 | 2025-01-02 | 2025-12-29 | 80.63% | 326644.6 |  | ON GOING
|  |  |  | DUJALI- NEW CASAY |  | 294620.48 | 2025-01-02 | 2025-12-29 | 6.115% | 18014.81 |  | ON GOING
|  |  |  | MENZI- BALAGUNAN-TULALIAN |  | 812003.41 | 2025-01-02 | 2025-12-29 | 67.96% | 551861.18 |  | ON GOING
|  |  | TOTAL REPAIRS & MAINT. OF PROVINCIAL ROADS-DIST. II |  |  | 29700000 |  |  |  | 16669646.08
INFRASTRUCTURE DEVELOPMENT PROGRAM
VARIOUS GOV'T BLDGS. & FACILITIES DEV'T PROJECT (4918)
|  |  |  | CONST. OF OPD COMPLEX, CARMEN DIST. HOSP., BRGY ISING, CARMEN | CARMEN | 15000000 |  |  | 0% | 0 |  | on going(0.43%)
|  |  |  | RENOVATION & EXPANSION OF LABORATORY AT DDN HOSP-KAPALONG ZONE (PHASE II), KAPALONG | KAPALONG | 5000000 |  |  | 15% | 749924.49 |  | on going (15%)
|  |  | TOTAL VARIOUS GOV'T BLDGS. & FACILITIES DEV'T PROJECT |  |  | 20000000 |  |  |  | 749924.49
VARIOUS GOV'T BLDGS. & FACILITIES DEV'T PROJECT (8918)
|  |  |  | CONST. OF LPRRC FENCE, LUNTIANG PARAISO, NEW CORELLA | NEW CORELLA | 6000000 | 03/20/2025 | 2025-06-09 | 0% | 0 |  | on going(42.55%)
|  |  |  | CONST. OF MULTI-PURPOSE BLDG, BARRACKS COMPOUND, BRGY. VISAYAN VILLAGE, TAGUM CITY | TAGUM CITY | 10000000 |  |  | 0% | 0 |  | on going(30%)
|  |  |  | CONST. OF LEGISLATIVE BLDG (PHASE III), TALAINGOD | TALAINGOD | 8000000 |  |  | 0% | 0 |  | procurement on process
|  |  |  | CONST. OF BRGY HALL, BRGY NAPUNGAS, ASUNCION | ASUNCION | 10000000 |  |  | 0% | 0 |  | procurement on process
|  |  |  | REHAB/ IMPVT. OF ROOFING/CEILING AT DDN SPORTS AND TOURISM COMPLEX (CONST. OF MPB), BRGY. MANKILAM, TAGUM CITY | TAGUM CITY | 1400000 | 2025-05-02 |  | 51.34% | 718790.3 |  | waiting for delivery of materials
|  |  |  | CONST. OF BRGY HALL (PHASE III). BRGY. DOÑA ANDREA ASUNCION | ASUNCION | 2400000 |  |  | 0% | 0 |  | procurement on process
|  |  |  | REPAIR/REHAB. OF PAVILION BLDG, DNSTC, TAGUM, CITY | TAGUM CITY | 1000000 |  |  | 5.775% | 57750 |  | procurement on process
|  |  |  | EXPANSION OF BAHAY SILANGAN (PHASE 4), GOV'T CENTER, BRGY. MANKILAM, TAGUM CITY | TAGUM CITY | 5000000 |  |  | 0% | 0 |  | on going(26%)
|  |  |  | CONST. OF 2ND ENGINEERING DIST. OFFICE AT NEW SITE (PHASE III), BRGY. TUGANAY, CARMEN | CARMEN | 5000000 |  |  | 0% | 0 |  | POW for Prep
|  |  |  | CONST. OF CAPUNGAGAN WAREHOUSE (PHASE II), BRGY. CAPUNGAGAN, KAPALONG | KAPALONG | 6000000 |  |  | 0% | 0 |  | procurement on process
|  |  |  | CONST. OF COMELEC BLDG. (PHASE IV), BRGY. MANKILAM, TAGUM CITY | TAGUM CITY | 1300000 |  |  | 0% | 0 |  | on going(45%)
|  |  |  | CONST. OF BRGY. HALL (PHASE III), BRGY. MAGATOS, ASUNCION | ASUNCION | 2500000 |  |  | 0% | 0 |  | procurement on process
|  |  |  | CONST. OF BRGY. HALL, BRGY. PANDAPAN, TAGUM CITY | TAGUM CITY | 10000000 | 03/20/2025 | 10/31/2025 | 0% | 0 |  | on going(41%)
|  |  |  | CONST. OF PEO 2ND ENGINEERING DIST-EQPT POOL REPAIR BAY, CARMEN | CARMEN | 5000000 |  |  | 0% | 0 |  | on going(21.07%)
|  |  |  | CONST. OF COVERED COURT W/ SITE DEV'T, BRGY. NEW SANTIAGO, ASUNCION | ASUNCION | 8000000 |  |  | 30.64% | 2451003.07 |  | on going(23.82%)
|  |  |  | CONST. OF DPRC MULTI-PURPOSE COVERED COURT, GOV'T CENTER, BRGY MANKILAM, TAGUM CITY | TAGUM CITY | 3000000 |  |  | 0% | 0 |  | procurement on process
|  |  | TOTAL VARIOUS GOV'T BLDGS. & FACILITIES DEV'T PROJECT |  |  | 84600000 |  |  |  | 3227543.37
VARIOUS LOCAL ROADS AND DRAINAGE DEV'T PROJ. (8918)
|  |  | REHAB/ IMPV'T OF MAGUPISING BRIDGE, BRGY. MAGUPISING, B.E. DUJALI |  | B.E. DUJALI | 5000000 |  |  | 0% | 0 |  | POW for signature
|  |  | TOTAL VARIOUS LOCAL ROADS AND DRAINAGE DEV'T PROJ. |  |  | 5000000 |  |  | 0% | 0
VARIOUS WATER SYSTEM DEV'T PROJECT (8918)
|  |  |  | CONST. OF WATER SYSTEM (PHASE II), BRGY. PANDAPAN, TAGUM CITY | TAGUM CITY | 1500000 | 02/05/2025 |  | 89.46% | 1341956.15 |  | on going(43.33%)
|  |  |  | CONST. OF RAINWATER COLLECTOR AT BALAI PIG IMMIMANAN, SITIO MESULONG, BRGY. STO NIÑO, TALAINGOD | TALAINGOD | 800000 | 02/05/2025 |  | 75.79% | 606333.2 |  | for Implementation
|  |  | TOTAL VARIOUS WATER SYSTEM DEV'T PROJECT |  |  | 2300000 |  |  | 84.71% | 1948289.35
ROAD OPENING PROJECT
|  |  | ROAD OPENING OF BDRY. SUA-ON TO PRK. 10 (PHASE II) BRGY. FLORIDA, KAPALONG |  | KAPALONG | 6000000 |  |  | 0% | 0 |  | on going(90%)
|  |  | ROAD OPENING OF PRK 7, MAGATOS TO BDRY. CAMONING, ASUNCION |  | ASUNCION | 1500000 | 02/05/2025 |  | 84.15% | 1262303 |  | on going (57.93%)
|  | TOTAL ROAD OPENING PROJECT |  |  |  | 7500000 |  |  |  | 1262303
RURAL ELECTRIFICATION (8918)
|  |  |  | INSTALLATION OF SOLAR STREET LIGHTS ALONG BDRY. TAGUM-BACA-NEW CORELLA PROV'L ROAD |  | 2000000 |  |  | 0% | 0 |  | POW for Signature
|  |  |  | INSTALLATION OF SOLAR STREET LIGHTS ALONG ANIBONGAN- SALVACION- CABAY-ANGAN PROV'L ROAD |  | 1400000 |  |  | 0% | 0 |  | POW for Signature
|  |  |  | RURAL ELECTRIFICATION FROM PRK 11 TO PRK 7, BRGY CAMANSA, ASUNCION |  | 2500000 |  |  | 0% | 0 |  | re-aligned. SB#2
|  |  |  | RURAL ELECTRIFICATION GOING TO BINANCIAN BRGY HALL, BRGY. BINANCIAN, ASUNCION |  | 1500000 |  |  | 0% | 0 |  | Procurement on process
|  |  | TOTAL RURAL ELECTRIFICATION |  |  | 7400000 |  |  |  | 0
SLOPE PROTECTION & LAND DEVELOPMENT PROJECT
|  |  |  | SLOPE PROTECTION ALONG PANDULIAN-JCT. SAN MIGUEL SEGMENT 3 PROV'L ROAD, SAN ISDRO |  | 25000000 |  |  | 29.98% | 7495027.31 |  | on going(32%)
|  |  | TOTAL SLOPE PROTECTION & LAND DEV'T PROJ. |  |  | 25000000 |  |  |  | 7495027.31
IMPROVEMENT OF PROV'L ROADS AND BRIDGES
|  |  |  | IMPV'T OF 1 UNIT STEEL BRIDGE ALONG DUJALI- TANGLAW PROV'L ROAD, B.E. DUJALI |  | 400000 | 2025-05-02 |  | 69.91% | 279647 |  | on going
|  |  |  | REHAB. OF DUJALI-BALISONG-MAGUPISING PROV'L ROAD, B.E. DUJALI |  | 7707440 | 2025-05-02 |  | 92.3% | 7113796.19 |  | on going
|  |  |  | ROAD UPGRADING OF MESAOY- JCT. MAHAYAHAY PROV'L ROAD (PHASE III), NEW CORELLA |  | 15000000 |  |  | 0% | 0 |  | procurement on process
|  |  |  | REHAB/ IMPV'T OF POBLACION-LIMBAAN-SUAWON-MACGUM FMR, NEW CORELLA, DAVAO DEL NORTE |  | 10000000 |  |  | 0% | 0 |  | POW for Signature
|  |  |  | REHAB./ IMPV'T OF SONLON- CAMANSA FMR,DDN |  | 8000000 |  |  | 0% | 0 |  | procurement on process
|  |  | TOTAL IMPROVEMENT OF PROV'L ROADS AND BRIDGES |  |  | 41107440 |  |  |  | 7393443.19
TOTAL ANNUAL BUDGET | [5 empty] | 584021400 |  |  |  | 197480540.54
SUPPLEMENTAL BUDGET:
INFRASTRUCTURE DEVELOPMENT PROGRAM
VARIOUS GOV'T BLDGS. & FACILITIES DEV'T PROJECT (4918)
|  |  |  | CONST. OF 1 UNIT GUARD HOUSE AT PHO-LPRRC COMPOUND, BRGY. PONLACION, NEW CORELLA |  | 500000 |  |  |  | 0 |  | POW for Signature
|  |  | TOTAL VARIOUS GOV'T BLDGS. & FACILITIES DEV'T PROJ |  |  | 500000
VARIOUS GOV'T BLDGS. & FACILITIES DEV'T PROJECT (8918)
|  |  |  | INSTALLATION OF SOLAR STREET LIGHTS, BRGY. PAG-ASA, KAPALONG |  | 950000 |  |  |  | 0 |  | POW for Signature
|  |  |  | CONST. OF SECONDARY SINGLE PHASE LINE FOR 5 UNITS BROOD/GROW POULTRY HOUSES, SITIO SALAWAO, BRGY. STO. NINO, TALAINGOD |  | 432000 |  |  |  | 0 |  | POW for Signature
|  |  | TOTAL VARIOUS GOV'T BLDGS. & FACILITIES DEV'T PROJ |  |  | 1382000
VARIOUS WATER SYSTEM DEV'T PROJECT (8918)
|  |  |  | POTABLE WATER SYSTEM AT BRGY. SAN REMEGIO, KAPUTIAN, IGACOS |  | 578331 |  |  |  | 0 |  | re-appropriation only, project for resumption
|  |  |  | IMPVT OF POTABLE WATER SYSTEM, PHASE III, BRGY. TORIL, BABAK, IGACOS |  | 950000 |  |  |  | 0 |  | procurement on process
|  |  | TOTAL VARIOUS WATER SYSTEM DEV'T PROJ |  |  | 1528331
IMPV'T OF PROVINCIAL ROADS & BRIDGES (8918)
ROAD NETWORKS
|  |  |  | REHAB./ IMPVT. ALONG SAN JUAN-TALISAY PROV'L ROAD |  | 5000000 |  |  |  | 0 |  | POW for Signature
|  |  |  | REHAB./IMPVT. ALONG LIMBAAN-MACGUM PROV'L ROAD |  | 5000000 |  |  |  | 0 |  | POW for Signature
|  |  |  | REHAB./IMPVT. ALONG DATU BALONG-PRK MAMALIAN PROV'L ROAD |  | 2000000 |  |  |  | 0 |  | POW for Signature
|  |  |  | REHAB./IMPVT. ALONG SONLON-NEW VISAYAS-CAMANSA PROV'L ROAD |  | 2000000 |  |  |  | 0 |  | POW for Signature
|  |  | OTHER INFRASTRUCTURE ASSETS | [8 empty] | POW for Signature
|  |  |  | REALIGNMENT OF ELECTRIC LINE ALONG DALIGDIGON-PAITON FMR WITH BRIDGE, TALAINGOD |  | 7000000 |  |  |  | 0 |  | POW for Signature
|  |  | TOTAL IMPV'T OF PROVINCIAL ROADS & BRIDGES |  |  | 21000000
SLOPE PROTECTION & LAND DEV'T PROJECT (8918)
|  |  |  | SLOPE PROTECTION ALONG STA. FE-MAMBING PROV'L ROAD |  | 5000000 |  |  |  | 0 |  | POW for Signature
|  |  | TOTAL SLOPE PROTECTION & LAND DEVELOPMENT PROJECT |  |  | 5000000
PRDP PROVINCIAL COUNTERPART (8918)
|  |  |  | REHABILITATION OF DALIGDIGON-PAITON FMR WITH BRIDGE, TALAINGOD |  | 40000000 |  |  |  | 0 |  | for transfer to trust fund. Waiting for approval
|  |  | TOTAL PRDP PROVINCIAL COUNTERPART |  |  | 40000000
TOTAL SUPPLEMENTAL BUDGET | [5 empty] | 69410331
GRAND TOTAL | [5 empty] | 653431731 |  |  |  | 197480540.54
|  |  |  | EMELIA C. PALERO CPA, MSLRG |  |  | EDWIN I. JUBAHIB MMPA
|  |  |  | Local Budget Officer |  | Governor

## SUMM
SUMMARY OF REPAIR & MAINTENANCE - DISTRICT 1
| REPAIRS & MAINTENANCE OF PROVINCIAL ROADS-DIST. I |  | APPROPRIATION |  |  | OBLIGATIONS
|  | Road Sections | Repairs & Maint. Infrastructure Asset | Fuel,Oil and Lubricants Expenses | TOTAL | Repairs & Maint. Infrastructure Asset | Fuel,Oil and Lubricants Expenses | TOTAL
|  | JCT. HIGHWAY MAGATOS - NEW BANTAYAN | 968974.54 |  | 968974.54 | 504092.27 |  | 504092.27
|  | MAGATOS - BDRY. PAGSABANGAN | 1136839.15 |  | 1136839.15 | 613048.5 |  | 613048.5
|  | ILOG - NEW BANTAYAN | 373678.14 |  | 373678.14 | 202668.64 |  | 202668.64
|  | ASUNCION - MONTE CARLO - DEL PILAR | 719297.52 |  | 719297.52 | 287952.54 |  | 287952.54
|  | JCT. HIGHWAY CANATAN - MAGATOS | 677313.65 |  | 677313.65 | 371317.57 |  | 371317.57
|  | SAUG-SONLON-BDRY. LONGANAPAN | 1192397.8 |  | 1192397.8 | 696286.1 |  | 696286.1
|  | JCT. NEW VISAYAS - BUAN | 329081.54 |  | 329081.54 | 176806.82 |  | 176806.82
|  | KAPALONG-MABANTAO-FLORIDA | 1045246.62 |  | 1045246.62 | 608629.05 |  | 608629.05
|  | JCT. HIGHWAY GABUYAN - SEMONG - DAGOHOY | 978439.76 |  | 978439.76 | 547019.25 |  | 547019.25
|  | SEMONG - PALMA GIL | 300465.75 |  | 300465.75 | 157642.95 |  | 157642.95
|  | STO. NIÑO-PALMA GIL-SITIO OPAO | 224149.64 |  | 224149.64 | 107018.67 |  | 107018.67
|  | DALIGDIGON-DAGOHOY | 143783.32 |  | 143783.32 | 45036.25 |  | 45036.25
|  | CAPUNGAGAN - MABUHAY - PANDULIAN | 637559.72 |  | 637559.72 | 358148.89 |  | 358148.89
|  | PANDULIAN - JCT. SAN MIGUEL | 196524.41 |  | 196524.41 | 92556.25 |  | 92556.25
|  | FLORIDA- NEW BOHOLANO | 237026.76 |  | 237026.76 | 102672.82 |  | 102672.82
|  | JCT. NEW BOHOLANO - NEW LOON | 587988.37 |  | 587988.37 | 311036.89 |  | 311036.89
|  | KM. 9, SAGAYEN-SAWATA | 794638.37 |  | 794638.37 | 473686.19 |  | 473686.19
|  | KM. 15, KIPALILI - NEW LOON | 958981.03 |  | 958981.03 | 499472.5 |  | 499472.5
|  | SAWATA-LIBUTON-MONTE DUJALI-PATEL | 1857736.84 |  | 1857736.84 | 1084938.07 |  | 1084938.07
|  | SAWATA-MAMANGAN-PINAMUNO | 1994652.37 |  | 1994652.37 | 1051671.81 |  | 1051671.81
|  | IGANGON - SAWATA | 404010.88 |  | 404010.88 | 132069.14 |  | 132069.14
|  | TAGAYTAY-BUAN | 571963.52 |  | 571963.52 | 397143.25 |  | 397143.25
|  | LIMBAAN-STA. FE- EL SALVADOR | 2251490.05 |  | 2251490.05 | 1692550.75 |  | 1692550.75
|  | DEL PILAR-JCT. SILANGAN | 569101.95 |  | 569101.95 | 377941.25 |  | 377941.25
|  | NEW CORELLA - NEW SAMBOG - SILANGAN | 700558.47 |  | 700558.47 | 473266.89 |  | 473266.89
|  | POB. NEW CORELLA - PRK. 10 POB. | 54369.99 |  | 54369.99 | 6426.25 |  | 6426.25
|  | PRK. 7 POB. - NEW SAMBOG | 257498.05 |  | 257498.05 | 158762.5 |  | 158762.5
|  | NEW CORELLA-GUADALUPE-DEL MONTE | 1247648.28 |  | 1247648.28 | 923164.5 |  | 923164.5
|  | STA. FE- DEL MONTE | 367602.79 |  | 367602.79 | 167113.75 |  | 167113.75
|  | NEW CORELLA- NEW BOHOL | 590651.84 |  | 590651.84 | 326862.3 |  | 326862.3
|  | CARCOR- JCT. KAUSWAGAN | 494480.78 |  | 494480.78 | 255906.21 |  | 255906.21
|  | DEL PILAR- PRK. 9 BAGSAK-SAN JOSE | 536039.71 |  | 536039.71 | 331948.14 |  | 331948.14
|  | SAN JUAN- NEW TALISAY | 700118.23 |  | 700118.23 | 405509.59 |  | 405509.59
|  | SAN JUAN- KAUSWAGAN- NEW CORTEZ | 142902.83 |  | 142902.83 | 19791.25 |  | 19791.25
|  | NEW BOHOL - JCT. EL UNIDO | 243894.55 |  | 243894.55 | 116019.25 |  | 116019.25
|  | NEW CORELLA- EL UNIDO- JCT. MESAOY | 960081.64 |  | 960081.64 | 470618.14 |  | 470618.14
|  | MESAOY-DASING | 189700.65 |  | 189700.65 | 97976.5 |  | 97976.5
|  | JCT. SAN JUAN- JCT. MESAOY | 224347.76 |  | 224347.76 | 97196.89 |  | 97196.89
|  | MESAOY- JCT. MAHAYAHAY | 575727.61 |  | 575727.61 | 272534.64 |  | 272534.64
|  | MESAOY- NEW BOHOL | 692766.17 |  | 692766.17 | 333764.75 |  | 333764.75
|  | NEW VISAYAS-BINANCIAN | 171034.35 |  | 171034.35 | 40356.73 |  | 40356.73
|  | DATU BALONG- PRK. MAMALIAN | 76162.02 |  | 76162.02 | 18974.49 |  | 18974.49
|  | PUROK 7 POBLACION-LIMBAAN | 167688.51 |  | 167688.51 | 37796.89 |  | 37796.89
|  | LIMBAAN- MACGUM | 196876.61 |  | 196876.61 | 9563.28 |  | 9563.28
|  | JCT. HIGHWAY CANATAN- DOÑA ANDREA | 592302.75 |  | 592302.75 | 393509.25 |  | 393509.25
|  | STA. FELOMINA- SAN ROQUE | 879076.94 |  | 879076.94 | 596152.5 |  | 596152.5
|  | JCT. SAGAYEN - SONLON | 1733302.19 |  | 1733302.19 | 1207661.22 |  | 1207661.22
|  | SAN VICENTE- BUTAY | 893560.94 |  | 893560.94 | 535223.05 |  | 535223.05
|  | JCT. HIGHWAY DOÑA ANDREA - CAPUNGAGAN | 1187335 |  | 1187335 | 771495.64 |  | 771495.64
|  | PAMACAUN- LASANG- BANATE | 412331.47 |  | 412331.47 | 290740.05 |  | 290740.05
|  | ANGELO - DAGOHOY | 48206.59 |  | 48206.59 | 5080 |  | 5080
|  | DALIGDIGON- LUMABAG | 310371.22 |  | 310371.22 | 195151.39 |  | 195151.39
|  | STO. NIÑO- DALIGDIGON- PAITON | 1317646.88 |  | 1317646.88 | 933517.17 |  | 933517.17
|  | JCT. PAITON- MIBOLO | 2735669.16 |  | 2735669.16 | 1862402.6 |  | 1862402.6
|  | JCT. SAMPAO- BDRY. MAMACAO | 679646.93 |  | 679646.93 | 461782.51 |  | 461782.51
|  | JCT. HIGHWAY LUNA- MAMACAO- NARRA | 918588.75 |  | 918588.75 | 546782.97 |  | 546782.97
|  | JCT. GABUYAN - KATIPUNAN - BUCANA | 726048.53 |  | 726048.53 | 416074.45 |  | 416074.45
|  | FLORIDA-SUAON- JCT. GUPITAN | 1893792.73 |  | 1893792.73 | 1356433.75 |  | 1356433.75
|  | JCT. SUAON - LIBUTON | 271673.87 |  | 271673.87 | 120670.25 |  | 120670.25
|  | JCT. DACUDAO- MABUHAY | 117016.55 |  | 117016.55 | 37558.75 |  | 37558.75
|  | MONTE DUJALI - GUPITAN | 433639.22 |  | 433639.22 | 226740 |  | 226740
|  | JCT. PATEL- LANGAN | 156902.56 |  | 156902.56 | 57122.43 |  | 57122.43
|  | DATU BALONG- PINAMUNO | 289503.71 |  | 289503.71 | 181262.49 |  | 181262.49
|  | JCT. SAWATA - BDRY. BINASBAS | 52653.05 |  | 52653.05 | 28292.89 |  | 28292.89
|  | NEW CORELLA- STO. NIÑO-MACGUM | 1515910.27 |  | 1515910.27 | 1039934.16 |  | 1039934.16
|  | STA. FE- MAMBING | 815065.63 |  | 815065.63 | 546643.97 |  | 546643.97
|  | NEW CORELLA- SAUG | 1009697.01 |  | 1009697.01 | 562875.39 |  | 562875.39
|  | LIMBAAN- STO NIÑO | 393224.93 |  | 393224.93 | 211868.14 |  | 211868.14
|  | JCT. MONTE CARLO - UPPER CABAYWA- CANATAN | 527454.98 |  | 527454.98 | 274637 |  | 274637
|  | CARCOR- PATROCENIO- JCT. BAYABAS | 1027172.01 |  | 1027172.01 | 726549.82 |  | 726549.82
|  | DEL PILAR-EL UNIDO | 110412.91 |  | 110412.91 | 45320 |  | 45320
|  | BRDY. TAGUM-BACA- NEW CORELLA | 646606.71 |  | 646606.71 | 404820.55 |  | 404820.55
|  | JCT. CARCOR - PRK. 9 BAGSAK | 264145.72 |  | 264145.72 | 150100 |  | 150100
|  | CARCOR- PUROK 7 POBLACION | 55734.75 |  | 55734.75 | 1600 |  | 1600
|  | ASUNCION- NEW ALEGRIA- BDRY. CUAMBOGAN | 267711.69 |  | 267711.69 | 146600 |  | 146600
|  | SONLON- NEW VISAYAS- CAMANSA | 199958.31 |  | 199958.31 | 100600 |  | 100600
|  | PRK. 1 MAUNLOM- PRK. 6 MAUNLOM | 376143.5 |  | 376143.5 | 204001.9 |  | 204001.9
[5 empty] | 50600000 |  |  | 30094163.65 | 0
REPAIRS & MAINTENANCE OF PROVINCIAL ROADS-DIST. II
|  | CEBULANO- MANGALCAL | 383927.31 |  | 383927.31 | 246552.53 |  | 246552.53
|  | TUBOD - BASA - MANGALCAL | 361830.78 |  | 361830.78 | 15972.44 |  | 15972.44
|  | JCT. HIGHWAY CARMEN-MANGALCAL-TUBOD | 1044061.33 |  | 1044061.33 | 785963.63 |  | 785963.63
|  | ISING-ST.NIÑO | 190582.62 |  | 190582.62 | 28525.71 |  | 28525.71
|  | TUGANAY-TABA | 393134.2 |  | 393134.2 | 372837.69 |  | 372837.69
|  | NEW CAMILING - ALEJAL - LOWER MAGSAYSAY | 619623.7 |  | 619623.7 | 480121.65 |  | 480121.65
|  | JCT HIGHWAY-TUGANAY-ANIBONGAN | 336972.17 |  | 336972.17 | 15972.45 |  | 15972.45
|  | MABAUS - CABAY-ANGAN | 294620.48 |  | 294620.48 | 31158.82 |  | 31158.82
|  | JCT. HIGHWAY GUADALUPE - BDRY. TAGUM | 727344.31 |  | 727344.31 | 590524.38 |  | 590524.38
|  | POBLACION DUJALI - PRK. 8 DUJALI | 754964.98 |  | 754964.98 | 740783.14 |  | 740783.14
|  | PRK 1- PRK 2 SITIO PAWAS | 128896.46 |  | 128896.46 | 13610.69 |  | 13610.69
|  | BACALI - CASIG-ANG - LIBERTAD | 432723.83 |  | 432723.83 | 330094.55 |  | 330094.55
|  | PRK.MAGSAYSAY- LUNGA-OG- DALISAY | 258713.61 |  | 258713.61 | 15972.44 |  | 15972.44
|  | PRK.APITONG-UPPER BALISONG-DALISAY | 423516.94 |  | 423516.94 | 15972.44 |  | 15972.44
|  | LOS AMIGOS 1 - ESPERANZA - LOS AMIGOS 2 | 330481.32 |  | 330481.32 | 15972.44 |  | 15972.44
|  | NEW KATIPUNAN- PANTARON | 180455.04 |  | 180455.04 | 10125.32 |  | 10125.32
|  | FD RD 3 - KIMAMON - LUNA | 1082730.26 |  | 1082730.26 | 669660.39 |  | 669660.39
|  | ISING- SADPODON- TABA- DILADILA | 522951.35 |  | 522951.35 | 309056.22 |  | 309056.22
|  | ALEJAL - ALEMAG | 164803.33 |  | 164803.33 | 0 |  | 0
|  | TUGANAY - ANIBONGAN - SAN ISIDRO | 664737.46 |  | 664737.46 | 552242.47 |  | 552242.47
|  | DALISAY - MABUHAY | 299223.93 |  | 299223.93 | 11651.74 |  | 11651.74
|  | DUJALI-BALISONG- MAGUPISING | 922780.17 |  | 922780.17 | 770850.2 |  | 770850.2
|  | DUJALI-SAN MIGUEL | 363672.16 |  | 363672.16 | 251177.17 |  | 251177.17
|  | UPPER MANGALCAL-LOWER MANGALCAL | 223727.43 |  | 223727.43 | 15972.44 |  | 15972.44
|  | CEBULANO - LOCETA | 172168.84 |  | 172168.84 | 21822.46 |  | 21822.46
|  | MALIGAYA-NEW CAMILING | 196106.76 |  | 196106.76 | 26702.64 |  | 26702.64
|  | ANAHAW- MALIGAYA | 441930.72 |  | 441930.72 | 70398.78 |  | 70398.78
|  | ANIBONGAN-GUADALUPE | 228330.87 |  | 228330.87 | 17655.34 |  | 17655.34
|  | JCT. ANIBONGAN- PRK 2,7,5 SAN ISIDRO | 289096.35 |  | 289096.35 | 16858.8 |  | 16858.8
|  | NEW CASAY - BUGTONG TALISAY | 200710.2 |  | 200710.2 | 15972.44 |  | 15972.44
|  | PRK. 5 RJS - PRK. 6 NEW CASAY | 251348.1 |  | 251348.1 | 161482.49 |  | 161482.49
|  | DUJALI SITIO PAWAS | 115086.13 |  | 115086.13 | 17790.85 |  | 17790.85
|  | DUJALI- PAWAS- SAN VICENTE | 406944.54 |  | 406944.54 | 34632.44 |  | 34632.44
|  | JCT. SALVACION- SAN VICENTE- CABAY-ANGAN | 317637.71 |  | 317637.71 | 56132.78 |  | 56132.78
|  | SAN MIGUEL - CASIG - ANG | 234775.7 |  | 234775.7 | 96928.2 |  | 96928.2
|  | KINAMAYAN - MOSLOG - MAHAYAG | 297382.55 |  | 297382.55 | 17300.28 |  | 17300.28
|  | SAN MIGUEL - MOSLOG KINAMAYAN | 266999.81 |  | 266999.81 | 16083.24 |  | 16083.24
|  | KINAMAYAN LUNGA-OG | 238458.45 |  | 238458.45 | 3113.41 |  | 3113.41
|  | SITIO PARADISE - MAGKAKAISA - ESPERANZA | 161120.58 |  | 161120.58 | 91109.55 |  | 91109.55
|  | MUGAS - LANATAD | 140865.42 |  | 140865.42 | 25973.74 |  | 25973.74
|  | MUGAS - LUNGA - OG | 246744.65 |  | 246744.65 | 20524.04 |  | 20524.04
|  | PANTARON - MUGAS | 308430.82 |  | 308430.82 | 15972.44 |  | 15972.44
|  | FD RD 3 SAN JOSE | 435489.5 |  | 435489.5 | 350306.1 |  | 350306.1
|  | NAFCO - BOBONGON | 244903.27 |  | 244903.27 | 6106.73 |  | 6106.73
|  | JCT. BDRY. TAGUM TALOMO | 786007.49 |  | 786007.49 | 776141.78 |  | 776141.78
|  | JCT. HIGHWAY-ST.NINO - CEBULANO | 192424 |  | 192424 | 0 |  | 0
|  | JCT. HIGHWAY - TUBOD - BAGONG SILANG | 172168.84 |  | 172168.84 | 15860 |  | 15860
|  | BASA-TUBOD | 143627.48 |  | 143627.48 | 17260 |  | 17260
|  | TUBOD - PILAR | 142706.8 |  | 142706.8 | 2954.55 |  | 2954.55
|  | LOCETA -LOWER MANGALCAL | 190582.62 |  | 190582.62 | 10686.28 |  | 10686.28
|  | LOWER ASUNCION - UPPER ASUNCION | 93910.28 |  | 93910.28 | 1772.73 |  | 1772.73
|  | JCT. HIGHWAY- ISING- MAGSAYSAY | 998026.88 |  | 998026.88 | 988161.17 |  | 988161.17
|  | ANIBONGAN- SALVACION- CABAY-ANGAN | 638037.48 |  | 638037.48 | 610709.57 |  | 610709.57
|  | MABAUS- SALVACION | 127055.08 |  | 127055.08 | 16910 |  | 16910
|  | SITIO MALAGA- TIBULAO | 296461.86 |  | 296461.86 | 286596.15 |  | 286596.15
|  | DUJALI- TANGLAW | 331448.04 |  | 331448.04 | 25969.93 |  | 25969.93
|  | DUJALI- SAN ISIDRO | 595946.7 |  | 595946.7 | 331110.25 |  | 331110.25
|  | CABAY-ANGAN - ESPERANZA | 494409.99 |  | 494409.99 | 412223.56 |  | 412223.56
|  | PRK 5- PRK. 1 PAWAS- DUJALI | 200710.2 |  | 200710.2 | 35038.34 |  | 35038.34
|  | PRK 6 CABAY-ANGAN- ESTI | 99434.41 |  | 99434.41 | 23924.41 |  | 23924.41
|  | PRK NARAFIL- BRGY SITE MAGUPISING | 191503.31 |  | 191503.31 | 26709.03 |  | 26709.03
|  | SAN MIGUEL - CROSSING KINAMAYAN | 257792.92 |  | 257792.92 | 10744.27 |  | 10744.27
|  | SAN MIGUEL - LIBERTAD | 570827.18 |  | 570827.18 | 560961.47 |  | 560961.47
|  | FD. RD. 2- STO. TOMAS- MAGWAWA | 940023.47 |  | 940023.47 | 930157.76 |  | 930157.76
|  | JCT. HIGHWAY- BUGTONG LUBI- BALAGUNAN | 255030.85 |  | 255030.85 | 17171.11 |  | 17171.11
|  | JCT. HIGHWAY- BALAGUNAN | 278968.77 |  | 278968.77 | 14725.46 |  | 14725.46
|  | JCT.HIGHWAY - TANGLAW | 366434.22 |  | 366434.22 | 315795.72 |  | 315795.72
|  | KIMAMON - LUNGA-OG - TALOMO | 551492.71 |  | 551492.71 | 541627 |  | 541627
|  | BDRY TAGUM- CROSSING KINAMAYAN- STO. TOMAS | 1332904.13 |  | 1332904.13 | 1254995.85 |  | 1254995.85
|  | PRK. NARAFIL- PRK. DAISY MAGUPISING | 69512.26 |  | 69512.26 | 14008.26 |  | 14008.26
|  | SAN JOSE- SITIO MAHAYAHAY,MAGWAWA | 196106.56 |  | 196106.56 | 0 |  | 0
|  | STO. TOMAS- BDRY. MAMACAO | 451137.61 |  | 451137.61 | 441271.9 |  | 441271.9
|  | JCT. HIGHWAY- STO. NIÑO- LA PAZ- SAN VICENTE | 559778.91 |  | 559778.91 | 409377.82 |  | 409377.82
|  | JCT. HIGHWAY- STO NIÑO- KABANKALAN- LA PAZ | 362795.76 |  | 362795.76 | 306623.42 |  | 306623.42
|  | JCT. HWAY- TUGANAY-TABA | 405103.16 |  | 405103.16 | 326644.6 |  | 326644.6
|  | DUJALI- NEW CASAY | 294620.48 |  | 294620.48 | 18014.81 |  | 18014.81
|  | MENZI- BALAGUNAN-TULALIAN | 812003.41 |  |  | 551861.18 |  | 551861.18
|  | TOTAL | 29700000 |  | 29700000 |  |  | 16669646.08 | 0
0